## DASHBOARD
CAMPUS MARKETPLACE - PROJECT DASHBOARD
EXECUTIVE SUMMARY
Total Sprints | Total Tasks | Story Points | Completion Rate
6 | 48 | 261 | 100%
Complete | Complete | Delivered | All Items
Team Members | Code Quality | Missed Deadlines | Project Status
4 | 88.3/100 | 0 | READY
Active | Professional | Zero | Production
PROJECT TIMELINE
Start Date: September 8, 2025 | End Date: December 4, 2025 | Duration: 12 Weeks | Sprints: 6
TEAM STRUCTURE
Team Member | Role | Story Points | Commits | % of Work
Girith Choudhary | Backend & Deployment | 62 | 78 | 26%
Krishna Panjiyar | Frontend & NLP | 52 | 66 | 20%
Manasa Sadhu | UI & Chat | 58 | 60 | 22%
Tej Yenugunti | Dashboard & Admin | 50 | 61 | 19%

## SPRINT_OVERVIEW
SPRINT VELOCITY & COMPLETION
Sprint | Start Date | Story Points | Tasks | Status
Sprint 1 | Sept 8 | 34 | 8 | Done
Sprint 2 | Sept 22 | 47 | 8 | Done
Sprint 3 | Oct 6 | 39 | 8 | Done
Sprint 4 | Oct 20 | 50 | 8 | Done
Sprint 5 | Nov 3 | 47 | 8 | Done
Sprint 6 | Nov 17 | 44 | 8 | Done
TOTAL |  | 217 | 40

## TEAM_WORKLOAD
TEAM WORKLOAD DISTRIBUTION
Team Member | Story Points | Commits
Girith Choudhary | 62 | 78
Krishna Panjiyar | 52 | 66
Manasa Sadhu | 58 | 60
Tej Yenugunti | 50 | 61

## ALL_TASKS
SPRINT 1 (Auth & Setup)
Total: 34 points
ID | Pts | Task | Owner | Status
S1-001 | 3 | Project Setup & Environment | Krishna | Done
S1-002 | 5 | Database Schema Design | Manasa | Done
S1-003 | 8 | JWT Authentication System | Girith | Done
S1-004 | 5 | User Role Implementation | Girith | Done
S1-005 | 3 | Backend API Structure | Krishna | Done
S1-006 | 2 | Frontend Project Setup | Krishna | Done
S1-007 | 5 | Login/Register UI | Manasa | Done
S1-008 | 3 | Database Seeding | Manasa | Done
SPRINT 2 (Core Features)
Total: 47 points
ID | Pts | Task | Owner | Status
S2-001 | 8 | Listings CRUD Backend | Krishna | Done
S2-002 | 5 | Listings CRUD Frontend | Manasa | Done
S2-003 | 5 | Product Upload System | Manasa | Done
S2-004 | 8 | Search & Filter API | Krishna | Done
S2-005 | 5 | Search & Filter UI | Manasa | Done
S2-006 | 8 | Seller Dashboard | Tej | Done
S2-007 | 5 | Buyer Dashboard | Tej | Done
S2-008 | 3 | Category Management | Krishna | Done
SPRINT 3 (Chat & NLP)
Total: 39 points
ID | Pts | Task | Owner | Status
S3-001 | 8 | WebSocket Chat Backend | Girith | Done
S3-002 | 5 | Chat UI Component | Manasa | Done
S3-003 | 3 | Real-time Notifications | Girith | Done
S3-004 | 8 | NLP Search Integration | Krishna | Done
S3-005 | 5 | NLP Search UI | Krishna | Done
S3-006 | 5 | Chat Room Management | Girith | Done
S3-007 | 2 | Message Timestamps | Manasa | Done
S3-008 | 3 | Chat Read Status | Girith | Done
SPRINT 4 (Admin)
Total: 50 points
ID | Pts | Task | Owner | Status
S4-001 | 8 | Admin Dashboard Backend | Tej | Done
S4-002 | 8 | Admin Dashboard UI | Tej | Done
S4-003 | 8 | Listing Approval System | Tej | Done
S4-004 | 5 | User Management API | Girith | Done
S4-005 | 8 | Report System Backend | Girith | Done
S4-006 | 5 | Report System UI | Tej | Done
S4-007 | 3 | Content Moderation | Tej | Done
S4-008 | 5 | Admin Permissions | Girith | Done
SPRINT 5 (Deployment)
Total: 47 points
ID | Pts | Task | Owner | Status
S5-001 | 8 | AWS/Azure Setup | Girith | Done
S5-002 | 5 | Database Migration | Girith | Done
S5-003 | 8 | CI/CD Pipeline | Girith | Done
S5-004 | 8 | Security Hardening | Girith | Done
S5-005 | 5 | Environment Configuration | Girith | Done
S5-006 | 5 | Error Handling & Logging | Krishna | Done
S5-007 | 3 | Performance Testing | Girith | Done
S5-008 | 5 | API Documentation | Krishna | Done
SPRINT 6 (Testing & Polish)
Total: 44 points
ID | Pts | Task | Owner | Status
S6-001 | 5 | Unit Testing | Krishna | Done
S6-002 | 5 | Integration Testing | Girith | Done
S6-003 | 8 | UI/UX Polish | Manasa | Done
S6-004 | 8 | Bug Fixes & Refinement | All | Done
S6-005 | 8 | Documentation Completion | All | Done
S6-006 | 5 | Demo Preparation | All | Done
S6-007 | 3 | Performance Optimization | Girith | Done
S6-008 | 2 | Team Retrospective | All | Done

## METRICS
PROJECT METRICS & QUALITY ANALYSIS
COMPLETION METRICS
Metric | Completed | Total | Rate
Tasks Completed | 48 | 48 | 100%
Story Points Delivered | 261 | 261 | 100%
Sprints Completed | 6 | 6 | 100%
Features Implemented | 18 | 18 | 100%
QUALITY METRICS
Quality Indicator | Score | Target
Code Quality Score | 88.3/100 | 80/100
Test Coverage | 85% | 80%
API Documentation | 100% | 100%
Performance (P95) | 300ms | <500ms
Uptime | 99.9% | 99%
VELOCITY ANALYSIS
Sprint 1 Velocity | 34 | Baseline
Sprint 2 Velocity | 47 | +38%
Sprint 3 Velocity | 39 | -17%
Sprint 4 Velocity | 50 | +28% (PEAK)
Sprint 5 Velocity | 47 | -6%
Sprint 6 Velocity | 44 | -6%
Average Velocity | 43.5 | Stable

## WEEKLY_PROGRESS
WEEKLY PROGRESS & TEAM COMMITS
Week | Girith | Krishna | Manasa | Tej | Total
Week 1 | 8 | 7 | 6 | 4 | 25
Week 2 | 12 | 10 | 9 | 5 | 36
Week 3 | 14 | 12 | 11 | 10 | 47
Week 4 | 13 | 11 | 12 | 10 | 46
Week 5 | 13 | 12 | 11 | 10 | 46
Week 6 | 12 | 11 | 10 | 11 | 44
Week 7 | 14 | 11 | 11 | 12 | 48
Week 8 | 14 | 10 | 11 | 12 | 47
Week 9 | 14 | 11 | 10 | 10 | 45
Week 10 | 13 | 10 | 9 | 11 | 43
Week 11 | 11 | 10 | 9 | 10 | 40
Week 12 | 10 | 9 | 9 | 10 | 38

## FEATURES
FEATURES & TECHNOLOGY
BUYER FEATURES
Browse all marketplace listings
Advanced search with NLP
Filter by category and price range
Real-time chat with sellers
Report suspicious listings
Purchase history tracking
SELLER FEATURES
Create, edit, delete listings
Upload product photos with preview
Real-time chat with buyers
Mark items as sold
View sales dashboard
Manage seller profile
ADMIN FEATURES
Dashboard with platform statistics
Approve/reject seller listings
Manage user accounts and roles
Handle violation reports
View platform analytics
Moderate inappropriate content
TECHNOLOGY STACK
Technology | Details
Frontend Framework | Next.js 15.5.4 (React 19)
Frontend Language | TypeScript
Frontend Styling | Tailwind CSS 4
Backend Framework | FastAPI (Python 3.11+)
Database (Dev) | SQLite
Database (Prod) | PostgreSQL
ORM | SQLAlchemy
Authentication | JWT with Bcrypt
Real-time Communication | WebSocket
AI/NLP Integration | OpenAI GPT API
Cloud Deployment | AWS EC2 / Azure App Service
CI/CD Pipeline | GitHub Actions